## Slide 1: So what are we proposing?
As this is our 40th year we believe that we can operate in some capacity come November 1st.
Taking into consideration the responses from our volunteer base, we are proposing a multiphase, 6 phase, reopening plan.
We will have dates attached to each phase based on a review process.
Prior to moving into each phase we will have a 3 step review process:
    60 Day
      Initial meeting within our reopening group to discuss climate and possibility of reopening.
      Release of sheets to volunteer base
    30 Day
      Utilizing Martha Crenshaw and the CDC guidelines to discuss best practices as to transition to next phase.
      Access sign ups to see if we can move into these phases safely.
    15 Day
      Look at the climate to ensure that we can safely move into the next phase.
      Approach the churches for a vote of comfort in moving forward.
    Move into Phase
      Lots of Communication for the 3 days prior as we access the climate to move.

## Slide 2: 6 Phase Reopening Plan
Phase 1
  Nov 1st opening
  Breakfast/ Lunch/ Dinner Ministry
Phase 2
  Jan 1st (review to begin Nov 1st)
  ¼ capacity of guests at one location with Dinner and Overnight
Phase 3
  Feb 1st (review to begin Dec 1st)
  ¼ capacity of guests at 2nd location with Dinner and Overnight

## Slide 3: 6 Phase Reopening Plan
Phase 4
  March 1st (review to begin Jan 1st)
  Capacity of 50% on each side
Phase 5
  Opening day 2021
  Capacity to 75% at each side
Phase 6
  Next Season
  Capacity to 100%

## Slide 4: Risk Management Plan
Risk | Risk Level | Action | Action Plan
Assessment of climate at the time of review | Low | Move into next phase review 15-day operating plan | Full phase transition plan to be written and sent to all parties so there is a clear structure to phase orientation
 | Medium | Move to next 30-day assessment | Detailed follow up of review listing red flag issues within the climate with a postponement of 1 month to a 30 day assessment.
 | High | Move next review to be a 60-day review | Phase review to be postponed 1 month and reset of review process.

## Slide 5: Implementation of Phase 1
We will initially distribute 50 bagged meals each evening starting on Nov 1st. This number may increase with need, but communication will be sent well in advance.
A street crew representative and volunteers will distribute the bagged meals each evening from the Shrine parking lot.
We will provide a tent and cones with a specified set out plan so that we can make sure everyone is socially distanced and that our guests and volunteers are as safe as possible. We will also have PPE on hand, including face shields for volunteers, but we encourage everyone to bring their own if possible.
The church will not be accessible during the evenings.
Bags are to arrive premade at 6pm each evening, distribution will be done in 15 minute intervals starting at 6:30pm to reduce the chances of people congregating.
All materials used in set up, including face shields will be sanitized before and after set up each day with and electrostatic sanitizer.
Safety is our number one priority, please see links on our website that further explain the steps we are taking.
As always, if you have any questions or need any further details, please feel free to reach out to any of our coordinators.
Notes: May require more than one slide